## Sheet1
Client Website Development Master Plan | Estimate
Project Kick-off | 0 days
Discovery Phase
Requirements gathering
Collect requirements | 5 days
Develop BRD | 15 days
Deliver BRD to Client for review | 0 days
Client reviews BRD | 5 days
Update BRD base on Client's feedbacks | 3 days
Client approves BRD | 0 days
UX/UI Development
Sprint 1
Build Wireframe | 5 days
Feedback wireframe | 2 days
Revise wireframe | 2 days
Approve wireframe | 0 days
Build layout Desktop | 5 days
Feedback layout Desktop | 2 days
Revise layout Desktop | 3 days
Design Desktop sprint 1 approved | 0 days
Build Layout Mobile | 4 days
Feedback layout Mobile | 2 days
Revise layout Mobile | 3 days
Design Mobile sprint 1 approved | 0 days
Sprint 2
Build Wireframe | 5 days
Feedback wireframe | 2 days
Revise wireframe | 3 days
Approve wireframe | 0 days
Build Layout Desktop | 5 days
Feedback layout Desktop | 2 days
Revise layout Desktop | 3 days
Design Desktop sprint 2 approved | 0 days
Build Layout Mobile | 4 days
Feedback layout Mobile | 2 days
Revise layout Mobile | 3 days
Design Mobile sprint 2 approved | 0 days
Front-end & Back-end Development
Sprint 1
Coding & Unit Testing | 15 days
Sprint 2
Coding & Unit Testing | 15 days
Execute SIT
Execute testing round 1 | 5 days
SIT Bugs Fix round 1 | 5 days
Execute testing round 2 | 5 days
SIT Bugs Fix round 2 | 5 days
Deliver to UAT | 0 days
UAT Execution
Execute UAT round 1 | 10 days
UAT Bugs Fix round 1 | 10 days
Execute UAT round 2 | 10 days
UAT Bugs Fix round 2 | 10 days
UAT Sign-off | 0 days
Go-live
Security Scan & Prepare Works for Go-live | 5 days
Support Go-Live | 5 days
Go-live Sign-off | 0 days